All,

Please see below for status of NDT inspection as of 7:30 PM on 6/14/2026. If you have any questions, please don't hesitate to reach out.

COMPLETE

IN PROGRESS

ISSUES NOTED

Other Issues

RECOVERY BOILER #2

Total initial data turned over to BSI is 100%. Verifications are complete. There were no issues noted in scope work, no tubes forecasted to be below ASME minimum before the next outage.

Discovery based on scope work:

- Economizer 1 (rear economizer), rear header, cold side tube 79 (rearmost, outermost tube) was cut out to visually inspect due to report SAC on RT. Indications were determined to be buildup in the tube, not SAC. Dutchman was installed at this location.

Discovery based on visual inspection:

- None reported at this time.

Scope of work:

Floor UT – 100% of initial data received. Verifications complete. No issues noted.

Front Wall UT –100% of initial data received. Verifications complete. No issues noted.

Front Wall MLO – 100% of initial data received. Verifications complete. No issues noted.

Rear Wall UT – 100% of initial data received. Verifications complete. No issues noted.

Rear Wall MLO – 100% of initial data received. Verifications complete. No issues noted.Left Wall UT – 100% of initial data received. Verifications complete. No issues noted.

Left Wall MLO – 100% of initial data received. Verifications complete. No issues noted.

Right Wall UT – 100% of initial data received. Verifications complete. No issues noted.

Right Wall MLO – 100% of initial data received. Verifications complete. No issues noted.

Nose Arch – 100% of initial data received. Verifications complete. No issues noted.

Sootblower Pass A – 100% of initial data received. Verifications Complete. No issues noted.

Sootblower Pass B – 100% of initial data received. Verifications complete. No issues noted.

Sootblower Pass C – 100% of initial data received. Verifications complete. No issues noted.

Sootblower Pass D – 100% of initial data received. Verifications complete. No issues noted.

Sootblower Pass E – 100% of initial data received. Verifications complete. No issues noted.

Sootblower Pass F – 100% of initial data received. Verifications complete. No issues noted.

Sootblower Pass G – 100% of initial data received. Verifications complete. No issues noted.

Sootblower Pass H – 100% of initial data received. Verifications complete. No issues noted

Sootblower Pass I –  100% of initial data received. Verifications complete. No issues noted

Superheater MLO –  100% of initial data received. Verifications complete. No issues noted.

Superheater UT – 100% of initial data received. Verifications complete. No issues noted.

Other scope items:

- PT  OF ALL LOWER FURNACE OPENINGS – SMELT SPOUTS, PRIMARY, SECONDARIES, BURNERS, LIQUOR GUNS, OB PORTS, AND LOWER FURNACE MANWAYS -REPORT RECEIVED

- RT OF ECONOMIZER AT ALL FOUR HEADERS –complete. Supsected SAC confirmed to be buildup, not SAC.

- SWUT SOOTBLOWER FLANGE TO LANCE WELD (H, I, A, B, C, D, E, F, G) – no report received

- SWUT SOOTBLOWER NOZZLE EXTENSION TO LANCE WELD (H, I, A, B, C, D, E) – no report received

- SWUT SOOTBLOWER NOZZLE EXTENSION TO NOZZLE WELD (H, I, A, B, C, D, E) – no report received

- UT OF LAST 6" OF LANCE TUBE (H, I, A, B, C, D, E) – report received. Tubes reported below 85% of nominal. Nominal was reported to be 0.219, 85% is 0.186”

  - Pass I

  - 72 – 0.183”

  - Pass A

  - 31 – 0.166”

  - Pass B

  - 14 – 0.177”

  - 53 – 0.182”

  - Pass F

  - 33 – 0.142”

  - 37 – 0.122”

  - 39 – 0.156”

  - 40 – 0.169”

  - Pass G

  - 41 – 0.081”

  - 42 - 0.133”

  - 43 – 0.184”

  - 46 – 0.179”

  - 47 – 0.183”

  - At Drum

  - 59 – 0.186”

- VT OF ALL NOZZLES (BSI) – complete

- WFMT EAST ID FAN– no report received

- WFMT WEST ID FAN– no report received

- WFMT SCRUBBER FAN– no report received

- DRY MAG PRIMARY FD FAN– no report received

- DRY MAG SECONDARY FD FAN– no report received

- DRY MAG TERTIARY FD FAN– no report received

- UT/PT MUD DRUM BLOW DOWN LINES– no report received

- UT RAPID DRAIN LINES– no report received

Punchlist

Item 37 – Lowest Pit depth test found remaining wall to be 0.196” (T-Min 0.144”)

Item 38 – complete. Lowest reading re-verified to be 0.165”. Tmin is 0.144 and flag is 0.149”.

Item 61 – In progress

Item 75 – no report received